## TechLauncher
At Risk | Sprint | Issue | Assigned To | Status | Completion | Story Points | Start | Finish | Feature Type | Duration | Issue Key | Comments | Predecessors
Learn how to use this template
|  | AGILE PROJECT: Virtual Control for the Research Graph |  |  | 0.83 |  | 2016-08-01 | 2016-11-11 |  | 75d
Sprints
|  | Sprint 1 - Week 4 |  | Complete | 1 | 32 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Neo4j + Playing around | Andy Xiang | Complete | 100% | 5 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Neo4j + Playing around | Hao Zhang | Complete | 100% | 5 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Neo4j + Playing around | Kun WANG | Complete | 100% | 5 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Neo4j + Playing around | Zhaolian Zhou | Complete | 100% | 5 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Gephi + Playing around | Andy Xiang | Complete | 100% | 3 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Gephi + Playing around | Hao Zhang | Complete | 100% | 3 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Gephi + Playing around | Kun WANG | Complete | 100% | 3 | 2016-08-01 | 2016-08-08 |  | 6d
| Sprint 1 | Install Gephi + Playing around | Zhaolian Zhou | Complete | 100% | 3 | 2016-08-01 | 2016-08-08 |  | 6d
|  | Sprint 2 - Week 5 |  | Complete | 1 | 52 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Test Neo4j Plugin for Gephi on Ubuntu | Zhaolian Zhou | Complete | 100% | 5 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Test Neo4j Plugin for Gephi on Ubuntu | Kun WANG | Complete | 100% | 5 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Test Neo4j Plugin for Gephi on Mac | Hao Zhang | Complete | 100% | 8 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Test Neo4j Plugin for Gephi on Mac | Kun WANG | Complete | 100% | 8 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Test Neo4j Plugin for Gephi on Windows | Andy Xiang | Complete | 100% | 8 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Test Neo4j Plugin for Gephi on Windows | Zhaolian Zhou | Complete | 100% | 8 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Import the Grid nodes into Neo4j as CSV | Hao Zhang | Complete | 100% | 5 | 2016-08-08 | 2016-08-15 |  | 6d
| Sprint 2 | Import the Grid nodes into Neo4j as CSV | Andy Xiang | Complete | 100% | 5 | 2016-08-08 | 2016-08-15 |  | 6d
|  | Sprint 3 - Week 6 |  | Complete | 0.69 | 55 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Add the scripts to the github | Hao Zhang | Complete | 100% | 2 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Convert RD-Switchboard Neo4j database to Research Graph Schema | Kun WANG | MoreActionRequired | 50% | 8
TRUE | Sprint 3 | Convert RD-Switchboard Neo4j database to Research Graph Schema | Andy Xiang | MoreActionRequired | 50% | 8 | 2016-08-15 | 2016-08-22 |  | 6d
TRUE | Sprint 3 | Project Blogpost | Hao Zhang | MoreActionRequired | 20% | 8 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Project Blogpost | Zhaolian Zhou | MoreActionRequired | 20% | 8 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Prepare slides for mid-term review | Kun WANG | MoreActionRequired | 50% | 8 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Prepare slides for mid-term review | Andy Xiang | MoreActionRequired | 50% | 5 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Does Gephi have API? | Hao Zhang | Complete | 100% | 2 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Does Gephi have API? | Kun WANG | Complete | 100% | 2 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Does Gephi have API? | Andy Xiang | Complete | 100% | 2 | 2016-08-15 | 2016-08-22 |  | 6d
| Sprint 3 | Does Gephi have API? | Zhaolian Zhou | Complete | 100% | 2 | 2016-08-15 | 2016-08-22 |  | 6d
|  | Sprint 4 - Week 7 |  | Complete | 0.99 | 62 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Write a Java program for crosswalk | Kun WANG | MoreActionRequired | 90% | 8 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Write a Java program for crosswalk | Andy Xiang | MoreActionRequired | 90% | 8 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Project Blogpost | Hao Zhang | Complete | 100% | 8 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Project Blogpost | Zhaolian Zhou | Complete | 100% | 8 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Prepare slides for mid-term review | Zhaolian Zhou | Complete | 100% | 3 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Prepare slides for mid-term review | Kun WANG | Complete | 100% | 3 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Prepare slides for mid-term review | Andy Xiang | Complete | 100% | 3 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Prepare slides for mid-term review | Hao Zhang | Complete | 100% | 3 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Do the personality test | Zhaolian Zhou | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Do the personality test | Kun WANG | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Do the personality test | Andy Xiang | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Do the personality test | Hao Zhang | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Install Neo4j shell tool | Hao Zhang | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Install Neo4j shell tool | Zhaolian Zhou | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Install Neo4j shell tool | Kun WANG | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Install Neo4j shell tool | Andy Xiang | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 4 | Collect links of all resources in Google Drive | Hao Zhang | Complete | 100% | 2 | 2016-08-22 | 2016-08-29 |  | 6d
|  | Sprint 5 |  | Complete | 0.93 | 59 | 2016-08-22 | 2016-09-05 |  | 11d
| Sprint 5 | Create Graph ML from part or all the R.Neo4j database (2.8GB) | Hao Zhang | MoreActionRequired | 80% | 21 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 5 | Successfully test the crosswalk for publications | Kun WANG | MoreActionRequired | 80% | 3 | 2016-08-22 | 2016-08-29 |  | 6d
| Sprint 5 | Successfully test the crosswalk for grants | Andy Xiang | MoreActionRequired | 80% | 3 | 2016-08-22 | 2016-08-29 |  | 6d
TRUE | Sprint 5 | Project Blogpost: Gephi / link references to the text | Zhaolian Zhou | Complete | 100% | 3 | 2016-08-29 | 2016-09-05 |  | 6d
TRUE | Sprint 5 | Profile: Andy | Andy Xiang | Complete | 100% | 2 | 2016-08-29 | 2016-09-05 |  | 6d
TRUE | Sprint 5 | Profile: Hao | Hao Zhang | Complete | 100% | 2 | 2016-08-29 | 2016-09-05 |  | 6d
TRUE | Sprint 5 | Profile: Kun | Kun WANG | Complete | 100% | 2 | 2016-08-29 | 2016-09-05 |  | 6d
TRUE | Sprint 5 | Profile: Zhaolian | Zhaolian Zhou | Complete | 100% | 2 | 2016-08-29 | 2016-09-05 |  | 6d
| Sprint 5 | School presentation (Wednesday 3-5:30) | All | Complete | 100% | 21 | 2016-08-29 | 2016-09-05 |  | 6d
|  | Sprint 6 |  | Complete | 100% | 30 | 2016-09-05 | 2016-09-08 |  | 4d
| Sprint 6 | Create GraphML from part or all the R.Neo4j database (2.8GB) | Hao Zhang | Complete | 100% |  | 2016-09-05 | 2016-09-07 |  | 3d
| Sprint 6 | Finalise the debugging for GraphML exporter | Hao Zhang | Complete | 100% | 8 | 2016-09-05 | 2016-09-07 |  | 3d
| Sprint 6 | Export graph for ANDS | Hao Zhang | Complete | 100% | 2 | 2016-09-05 | 2016-09-07 |  | 3d
| Sprint 6 | Export graph for Dryad | Hao Zhang | Complete | 100% | 2 | 2016-09-05 | 2016-09-07 |  | 3d
| Sprint 6 | Successfully test the crosswalk | Kun WANG | Complete | 100% |  | 2016-09-05 | 2016-09-06 |  | 2d
| Sprint 6 | Publication (convert all records and test the data) | Kun WANG | Complete | 100% | 2 | 2016-09-05 | 2016-09-06 |  | 2d
| Sprint 6 | Datasets | Kun WANG | Complete | 100% | 3 | 2016-09-05 | 2016-09-06 |  | 2d
| Sprint 6 | Researcher | Andy Xiang | Complete | 100% | 3 | 2016-09-05 | 2016-09-06 |  | 2d
| Sprint 6 | Grant | Andy Xiang | Complete | 100% | 2 | 2016-09-05 | 2016-09-06 |  | 2d
| Sprint 6 | Setup hello world project using Leap Motion | Zhaolian Zhou | Complete | 1 |  | 2016-09-05 | 2016-09-08 |  | 4d
| Sprint 6 | Check to see if there is a code available for the leapmotion hello prog. | Zhaolian Zhou | Complete | 100% | 8 | 2016-09-05 | 2016-09-08 |  | 4d
| Sprint 7 | Sprint 7 |  | Complete | 0.99 | 54 | 2016-09-12 | 2016-09-15 |  | 4d
| Sprint 7 | Gephi: Investigate if there are options to visualise 50,000 records | Andy Xiang | Complete | 100% | 2 | 2016-09-12 | 2016-09-15 |  | 4d
| Sprint 7 | Investigate Cytoscape | Hao Zhang |  | 0 | 0
| Sprint 7 | Install Cytoscape | Hao Zhang | Complete | 100% | 2
| Sprint 7 | Import graphML file for ANDS | Hao Zhang | Complete | 100% | 3
| Sprint 7 | Test if we can have a force based graph visualiation | Hao Zhang | MoreActionRequired | 50% | 5
| Sprint 7 | Check for Tableau plugin | Zhaolian Zhou |  | 0 | 0
| Sprint 7 | Install Tableau demo | Zhaolian Zhou | MoreActionRequired | 0% | 5
| Sprint 7 | Install Neo4j driver | Zhaolian Zhou | MoreActionRequired | 70% | 8
| Sprint 7 | Import ANDS records from the database | Zhaolian Zhou | MoreActionRequired | 0% | 8
| Sprint 7 | Write a test program that changes graph layout using basic LeapMotion interaction |  |  | 0 | 0
| Sprint 7 | Write a java program to change Gephi layout | Andy Xiang | MoreActionRequired | 70% | 8
| Sprint 7 | Connect the Java program to LeapMotion | Kun WANG | MoreActionRequired | 10% | 8
| Sprint 7 | Refactoring Github |  |  | 1
| Sprint 7 | Leap Motion Sample - Add project and folder | Zhaolian Zhou | Complete | 100% | 3
| Sprint 7 | Crosswalk program - Add project and folder | Andy Xiang | Complete | 100% | 2
| Sprint 8 | Sprint 8 - Week 9 |  | Complete | 1 | 34 | 2016-09-21 | 2016-09-28 |  | 6d
| Sprint 8 | Meeting in Canberra (Wednesday 21 Sep) | ALL | Complete | 100% | 5 | 2016-09-21 | 2016-09-28 |  | 6d
| Sprint 8 | Check for Tableau plugin | Zhaolian Zhou | Complete | 1 | 0 | 2016-09-21 | 2016-09-28 |  | 6d
| Sprint 8 | Install Tableau demo | Zhaolian Zhou | Complete | 100% | 5 | 2016-09-21 | 2016-09-28 |  | 6d
| Sprint 8 | Install Neo4j driver | Zhaolian Zhou | Complete | 100% | 8 | 2016-09-21 | 2016-09-28 |  | 6d
| Sprint 8 | Explore the feasibility of connecting LeapMotion to Gephi |  | Complete | 1 | 0 | 2016-09-21 | 2016-09-28 |  | 6d
TRUE | Sprint 8 | Compile Gephi | Kun WANG | Complete | 100% | 8 | 2016-09-21 | 2016-09-28 |  | 6d
| Sprint 8 | Create a Java program for Gesture | Andy Xiang | Complete | 100% | 8 | 2016-09-21 | 2016-09-28 |  | 6d
demo of defining/creating a new Gesture?
| Sprint 9 | Sprint 9 - Week 10 |  | Complete | 1 | 37 | 2016-09-26 | 2016-10-03 |  | 6d
| Sprint 9 | Import ANDS records into Tableau | Zhaolian Zhou | Complete | 100% | 13 | 2016-09-26 | 2016-10-03 |  | 6d
| Sprint 9 | Created a new plugin for the Gephi | Kun WANG | Complete | 100% | 8 | 2016-09-26 | 2016-10-03 |  | 6d
| Sprint 9 | Created a new plugin for the Gephi | Hao Zhang | Complete | 100% | 8 | 2016-09-26 | 2016-10-03 |  | 6d
| Sprint 9 | Demo of defining/creating a new Gesture? | Andy Xiang | Complete | 100% | 8 | 2016-09-26 | 2016-10-03 |  | 6d
| Sprint 10 | Sprint 10 - Week 11 |  | Complete | 0.42 | 37 | 2016-10-10 | 2016-10-14 |  | 5d
| Sprint 10 | Create report on Tableau about the overall content of the Research Graph database | Zhaolian Zhou | MoreActionRequired | 0 | 8 | 2016-10-10 | 2016-10-14 |  | 5d
| Sprint 10 | Add the LeapMotion Sample to the Gephi plugin | Kun WANG | MoreActionRequired | 20% | 8 | 2016-10-10 | 2016-10-14 |  | 5d
| Sprint 10 | Trigger the layout transition from the plugin | Hao Zhang | Complete | 100% | 13 | 2016-10-10 | 2016-10-14 |  | 5d
| Sprint 10 | Create a gesture for the flip of the hand | Andy Xiang | MoreActionRequired | 70% | 5 | 2016-10-10 | 2016-10-14 |  | 5d
| Sprint 10 | Come up with one Gesture and the related action in Gephi | All | MoreActionRequired | 20% | 3 | 2016-10-10 | 2016-10-14 |  | 5d
| Sprint 11 | Sprint 11 - Week 12 |  |  | 0.88 | 42 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Define the data to be exported from Neo4j to Tableau | Amir Aryani | Complete | 100% | 2 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Create a CSV Exporter from Neo4j to Tableau | Zhaolian Zhou | MoreActionRequired | 50% | 5 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Use LeapMotion existing gesture to trigger the layout | Hao Zhang | MoreActionRequired | 50% | 13 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Create a gesture for the flip of the hand: Complete the Gesture Module | Andy Xiang | Complete | 100% | 8 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Create a gesture for the flip of the hand: Complete the Gesture Module | Kun WANG | Complete | 100% | 8 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Create poster about Research Graph Virtual Demo | Andy Xiang | Complete | 100% | 3 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Create poster about Research Graph Virtual Demo | Kun WANG | Complete | 100% | 3 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 11 | Come up with one Gesture and the related action in Gephi | All-Andy | Complete | 100% | 3 | 2016-10-17 | 2016-10-21 |  | 5d
| Sprint 12 | Sprint 12 - Week 13 |  |  | 0.75 | 24 | 2016-10-24 | 2016-10-28 |  | 5d
| Sprint 12 | Use LeapMotion existing gesture to trigger the layout | Hao Zhang | Complete | 100% | 8 | 2016-10-24 | 2016-10-28 |  | 5d
| Sprint 12 | Use LeapMotion existing gesture to trigger the layout | Andy Xiang | Complete | 100% | 8 | 2016-10-24 | 2016-10-28 |  | 5d
| Sprint 12 | Upload the dependencies for the crosswalk project | Kun WANG | In Progress |  | 3 | 2016-10-24 | 2016-10-28 |  | 5d
| Sprint 12 | Create a CSV Exporter from Neo4j to Tableau | Zhaolian Zhou | Complete | 100% | 5 | 2016-10-24 | 2016-10-28 |  | 5d
| Sprint 13 | Sprint 13 - (Amir was travelling)
| Sprint 14 | Spring 14 |  |  |  | 38 | 2016-11-07 | 2016-11-11 |  | 5d
| Sprint 14 | Test the Gephi and LeapMotion integration on Windows | Andy Xiang | In Progress |  | 3 | 2016-11-07 | 2016-11-11 |  | 5d
| Sprint 14 | Create a report of all the activities this Semester | All |  |  | 8
| Sprint 14 | Implement leapmotion layout demo | Hao Zhang |  |  | 8
| Sprint 14 | Implement leapmotion zoom in and out function | Andy Xiang |  |  | 8
| Sprint 14 | Creating slides for the semester 1 talk | All |  |  | 8
| Sprint 14 | Create a sample data for the demo | Amir Aryani |  |  | 3
| Sprint 15 | Sprint 15 - Week 6 (End of Semester Demo)
| Sprint 15 | End of Semester Demo
| Backlog | Backlogs
| Backlog | Gephi alternatives
| Backlog | Neo4j
| Backlog | Write a Java program to create GraphML
| Backlog | Type1 : source - node type - number of connections
| Backlog | Data Transformation
| Backlog | Import the Grid relationships into Neo4j |  | Not Started |  | 13
| Backlog | Import Research Graph version 1.2 into Gephi |  | Not Started
| Backlog | Import figshare |  | Not Started
| Backlog | Import NIH |  | Not Started
| Backlog | Import ARC and NHMRC data |  | Not Started
| Backlog | Connection Neo4j to Gephi |  | Not Started
| Backlog | Connection between Gephi and LeapMotion |  | Not Started
| Backlog | Write a test program that zoom the graph in and out |  | Not Started
| Backlog | Communication and Presentations |  | Not Started
| Backlog | Initial presentation about the project to the international partners |  | Not Started
| Backlog | Gephi: Demo of the first research graph |  | Not Started
| Backlog | LeapMotion: Demo the fist integration of Gephi and Leapmotion |  | Not Started
| Backlog | Blogpost: challenge of visualising 100,000 nodes

## Comments
Row 21 | https://www.grid.ac/ | Amir Aryani | 08/08/16 5:58 PM
Row 73 | https://developer.leapmotion.com/documentation/python/devguide/Sample_Tutorial.html | Amir Aryani | 15/08/16 4:53 PM
Row 79 | Dryad imports fine and smoother than in Gephi however always stuck when importing ands. | Hao Zhang | 18/09/16 10:35 PM
Row 98 | In org-gephi-layout-api.jar, there is an interface called LayoutContriller | Kun WANG | 20/09/16 8:14 PM
Row 98 | In org-gephi-visualization-api.jar, there is an interface called VisualizationController | Kun WANG | 20/09/16 8:19 PM
Row 98 | In org-gephi-graph-api.jar there is an interface called GraphController | Kun WANG | 20/09/16 8:21 PM
Row 107 | https://github.com/researchgraph/Virtual-Control/blob/master/LeapMotion/src/Sample.java | Amir Aryani | 06/10/16 6:46 PM
Row 110 | Andy: gesture the same as zoom in and out for opening and closing graph | Amir Aryani | 17/10/16 5:58 PM
Row 112 | The number of connections between two labels with one, two and three degrees of separation. | Amir Aryani | 20/10/16 7:26 PM
Row 119 | Amir: close the fist to stop the layout transition Amir: swipe left and right to add or remove filter for the degrees of nodes Amir: rotate the finger to zoom in and out | Amir Aryani | 24/10/16 4:57 PM
Row 119 | Kun: Opening and closing the fist toward the screen for zoom in and out | Amir Aryani | 24/10/16 5:04 PM
Row 119 | Kun: Move the hand toward leapmotion | Amir Aryani | 24/10/16 5:08 PM
Row 127 | works fine on windwos | Andy Xiang | 31/10/16 5:11 PM
Row 151 | This requires 1) import Neo4j to Gephi 2) convert RD-Switchboard Neo4j database to Research Graph Schema | Amir Aryani | 15/08/16 2:37 PM